## Slide 1: Programme Mgt Case Study
Energy Company

## Slide 2: Case Study
Contents
  Executive Summary
  Project History
  Contract Review
  Project Reporting
  Project Governance
  The Supplier
  Business Readiness
  Financial Performance & Benefits
  Training
  Conclusions & Recommendations

## Slide 3: Executive Summary
An Energy company set out to implement a HR system across multiple companies (mainly acquired and with disparate cultures).
There was no history of cooperation between group companies
There was a culture of “do your own thing” with respect to systems
It is remarkable, given the odds stacked against the project that it was ever implemented
  The project was high risk in trying to achieved common processes and systems – such projects had previously failed
  Whilst it was not perfectly managed, it partially met its objectives (common processes are not yet fully implemented), and in that sense, the project was “successful”
In terms of the IP, the project over spent the budget. However the objectives of the project changed materially throughout its life (for example self service HR assumed much more importance latterly) and in that sense the original budget was meaningless

## Slide 4: Executive Summary
The project was heading towards failure until a change of sponsor. Other changes made to the project at that time had an effect:
  Communication from the project greatly improved
  The revised project organisation worked better and there were clearer accountabilities
  More business resources were deployed
  It is doubtful that the project would have succeeded to the same degree had the action not been taken
  On the downside, team morale was damaged by the new operating style and it is doubtful whether the change would have been effective long term
  However, it gave the businesses an opportunity to vent their frustrations (many of their own making) and as such allowed the project to take away the “excuses” put up by the businesses
  It is unclear whether the businesses were truly bought into the go-live decision but that is now immaterial

## Slide 5: Executive Summary
The project was heading towards failure until a change of sponsor. Other changes made to the project at that time had an effect:
  The Supplier made much capital out of the changes, it is doubtful whether this was to XX Energy’s advantage
  A “big 5” consulting company were brought in at the last minute: it is not clear in hindsight what value they added
The Supplier was generally an effective partner, though many frustrations exist within XX Energy at The Supplier’s performance, many but not all of these are difficult to justify

## Slide 6: Project History
The project has a long history that contributed to the difficulties that were experienced
  There were multiple project managers and multiple attempts to re-launch the project which damaged the credibility of the project and the project team
  It is unclear how The Supplier came to be selected after the withdrawal of the original supplier (though this does not necessarily mean that The Supplier was a bad choice)
  The business became cynical that the project would ever be delivered so there was a convenient excuse for the businesses not to engage
  The IP was probably invalid by the time the project was started in summer of 2001 (both from a cost and benefits perspective)
  The long flirtation with an alternative supplier and confusion about the desire for outsourcing (or not) did not help the team to focus

## Slide 7: Project History
The project has a long history that contributed to the difficulties that were experienced
  The project was high risk because
    There were two legacy systems – the impact of this was inadequately understood until testing began – no one really understood the amount of customisation that had been made to both legacy systems
    It was the first time that XX Energy had tried to run a cross business project of this magnitude and process impact
      It is debatable whether the size of this challenge was fully appreciated
      Previous attempts at standardisation had foundered
      Certain businesses (such as YYY had a history of non-compliance)

## Slide 8: Project History
The project has a long history that contributed to the difficulties that were experienced
  A number of key risks were identified by us early on:
    Lack of XX Energy resources
    Lack of Business buy in to the project
    Lack of business champion
    The Supplier resources (lack of)
    Lack of authority/stature within the project to make and take key decisions
    Lack of communication within the business from key managers to and from business staff involved in the project
    Potential impact sponsor’s collegiate style
    Potential Impact of Phase 2 on the project
  It is fair to say that all these risks (except perhaps The Supplier resources) materially impacted the project at some point
  Additionally a further risk – scope creep – impacted the project

## Slide 9: Contract Review
The contractual arrangements (and penalty clauses) may have contributed to dysfunctional behaviour on the part of the supplier
  The mixture of “fixed”, “capped”, and “T&M” pricing models, at the time may have seemed a sensible way to mitigate the risk associated with some customisation, in fact allowed The Supplier a sufficient number of open ended buckets to lay off most of their risk should they have desired so to do.
    It is interesting to note that the fixed prices and capped price buckets were never, apparently, over spent
  There were, finally, 5 contractual instruments: this arrangement did not benefit XX Energy

## Slide 10: Project Reporting/Communication
From the start of the project onwards the project team issued weekly reports, issue logs, risk registers, and key actions lists
  The reports were representative (but probably over optimistic at times)
  They were formulated according to good practice
  These were summarised for the Steering Group but probably not circulated widely
  It is clear that these reports showed that there were certain key issues (such as lack of business engagement and lack of resources)
  It is also clear from the minutes that the issues were raised at the monthly steering group meetings
  It would appear that the the Steering Group either a) did not act upon the reports until late in the project or b) the action which was in some cases taken was ineffective

## Slide 11: Project Reporting/Communication
The project “communicated” to the business in many ways but most of it was “outbound”, “fire and forget”
  In hindsight the specifications that the businesses were asked to sign off were both too detailed and too high level (a neat trick)
    Too detailed in that they were highly technical in places
    Too high level in that they did not adequately describe the process impact of the functionality
    There is evidence that key business users did not read the specifications and felt under pressure to “sign”
There was an assumption by the project team that no response meant an affirmative response
The sheer volume of largely untargeted communication made it easy for business managers, that were in any case not fully engaged, to miss key messages

## Slide 12: Project Reporting/Communication
There are many, documented, incidents of business managers “signing off” (for example) process changes, only to recant their agreement at a later date
  At this distance, we can only speculate whether this was due to a lack of understanding on their part of the impact of original decision or to some other reason

## Slide 13: Project Organisation/Governance
Neither IT nor the business properly “owned” the project, thus the project lack support from both quarters. Also the perceived XX Energy versus YYY bias in the project team increased the lack of engagement
There was no commonly understood and agreed strategy underpinning the project – there were multiple agendas and little understanding of the “one XX Energy” message coming from the board
The Steering Group (SG), when re-constituted at the start, had appropriate representation according to good practice
  As discussed elsewhere, it was not always effective
  The Project Team (PT) believes it was given mixed messages by the SG on cost, resources, and the conflict between Phase 1 and 2
  The SG should have taken a more active role in educating and selecting the project team members

## Slide 14: Project Organisation/Governance
The Project Working Group (PWG) was ill conceived and ineffective
  In hindsight, its membership was too junior and had conflicting agendas driven by a desire to fight the corner of the business represented
In hindsight, the Programme Manager should have had executive authority: the role as constituted in an advisory capacity was not wholly effective
The PT, in hindsight, was too junior in its membership (particularly in HR) and was ill represented by YYY (where payroll was significantly more complex).
  Many of the complexities simply did not materialise until testing was underway
  Some PT members were not able to perform their duties as they were pulled back into the business at key times.

## Slide 15: Project Organisation/Governance
There was, effectively, a decision making void: the PWG was not capable of taking decisions and so the the PT, in good faith, took ownership of key decisions - not always correctly
Phase 2 (Advance Functionality) impacted the project materially
  Resources were diverted by The Supplier to Phase 2 activities using a serious of small T&M work work orders that bypassed the contractual arrangements
  There was no effective process to allocate resources across the two streams
There was no formal methodology used by the project – The Supplier used an in house methodology which the XX Energy project team acquiesced with – no thought was given to the appropriate approach
QA reviews were not effective – the SG found them unwelcome and in any case they did not get to the root cause of issues

## Slide 16: Project Organisation/Governance
Customisation was inadequately controlled. There was no effective process to agree and prioritise customisation. The project mantra was supposed to be “no customisation”
  In so far as we can see at this distance, customisation decisions were taken somewhat randomly by the project team when they could not broker an agreement with the business users
  The Steering Group was rarely consulted
  The scope of individual customisations was poorly understood and changed materially during testing
  The Supplier appeared somewhat literal in their interpretation of requirements, or perhaps failed to ask the right questions
  There was an almost pathological desire to customise The Supplier’s Advance Functionality toolset for Phase 2 (which to some degree still exists) for no really good reason that we can see

## Slide 17: Project Organisation/Governance
There was a large amount of scope creep – there was considerable pressure from the SG to add deliverables to Phase 1 (such as “simple” Advance Functionality items such as payslip on line). Whilst laudable in aim – this materially impacted the project
The issues of lack of business resources (and by implication lack of business buy in) were not confronted until the end
  The project team did their best to cajole and to make up for the lack of business support. They assumed responsibilities and made decisions in good faith on the basis of “if we don’t do it no one will”. In hindsight this course was, perhaps, mistaken – some decisions taken were later seen to be wrong and it did not help in “red flagging” issues
  The Steering Group failed to grasp, for whatever reason, how severe the problem was

## Slide 18: The Supplier
As discussed earlier the project was high risk and The Supplier had their reputation riding on it. In the final analysis, the project was delivered, a couple of months late all be it, and so far as anyone can tell staff have been paid correctly – in fact it highlighted errors in the legacy systems
The The Supplier project manager is regarded as largely responsible for the success of the project by both The Supplier and some XX Energy people, though this probably overplays the contribution
XX Energy should have taken more care & involvement in selecting The Supplier consultants to work on the project and been more rigorous in ensuring consistent quality – in addition the confused reporting lines between the 3rd party writing reports, The Supplier and XX Energy contributed to poor quality in this area

## Slide 19: The Supplier
It is difficult to criticise The Supplier too strongly in the above light, however the following observations are worth tabling (cont)
  The Supplier were not represented at the Steering Group – it is doubtful that this served the project well or at all
  The Supplier felt that they were pressured to divert resources to Phase 2 though it should be noted that the contractual arrangements made this switch advantageous for them
  The financial reporting of days spent against various buckets on Phase 1 was less than useful and difficult to challenge. As already discussed, the different types of buckets made it possible to switch one bucket to another

## Slide 20: The Supplier
It is difficult to criticise The Supplier too strongly in the above light, however the following observations are worth tabling (cont)
  There is a view that The Supplier were insufficiently challenging to XX Energy’s position – unwilling or unable to introduce best practice
  There is a belief that the quality of the The Supplier staff deployed was variable – this may have contributed to some of the difficulties extracting the correct information about customisation requirements for example
  The process for undertaking and assuming responsibility for customisation (especially joint developments) was flawed
  The 3rd party recommended by The Supplier to be contracted by XX Energy to deliver reporting requirements are not believed to have delivered: The Supplier must bear some moral responsibility for this

## Slide 21: The Supplier
It is difficult to criticise The Supplier too strongly in the above light, however the following observations are worth tabling (cont)
  The Supplier would argue that they have deployed significantly more effort than nominally charged for and it is difficult to argue this. However it must be noted that the current arrangement for maintenance and support and ongoing Advance Functionality development favour The Supplier
  The personal style of some of the The Supplier personnel and management structure was not always effective in the XX Energy environment – It seemed necessary to resort to intervention of the The Supplier account manager (and though she was effective, it bypassed line management)
  There are issues with the managed service that need to be addressed – upgrades for example seem to cause bugs and other unpredictable consequences

## Slide 22: Business Readiness
The Business Readiness stream was ineffective throughout (until re-organised near the end of the project)
  It was unrealistic to expect the stream to be managed by a managers with already full time commitments
  The issue of business ownership was never really bottomed out. Despite being raided regularly in the weekly reporting and at the Steering Group and despite action being taken by the Steering group, the action was largely ineffective because
    Resources promised did not materialise or were ineffective
    Certain individuals were fatally hampered by their overall workload and the team they delegated to delivered to an inconsistently level

## Slide 23: Business Readiness
The Business Readiness stream was ineffective throughout (until re-organised near the end of the project)
  The project team as a consequence had to “own” issues such as reporting to prevent slippage: some decisions they took in good faith were proven later to be ill conceived
  As a consequence, there was a risk (that materialised) that the configuration specification would miss a requirement, which would only come out in the training or later. Much remedial work had to be done at the end of the initial project and later to address this
  It appears in hindsight that decisions were made (as delegated by the Steering Group) that were for whatever reason not fully bought into by the businesses
  There were difficult decisions that the businesses avoided and hope would go away (like changes to the business processes)

## Slide 24: Business Readiness
The Business Readiness stream was ineffective throughout (until re-organised near the end of the project)
  There may have been a lack of full understanding by the businesses of the impact of some of the decisions and certainly of the impact of “agreed” process changes
  There was inadequate understanding of (or lack of access to) people who truly understood the legacy environment (and the incumbent business processes & complexities) so a number of key process issues did not become apparent until UAT

## Slide 25: Financial Performance & Benefits Review
It is unclear what benefits can be gained by a detailed analysis of the project spend because:
  It is impossible at this distance to be certain what was charged to each code with invoice analysis
  There may have been teaming and ladling of budgets
  The project objectives & scope changed
  The cost of Advance Functionality was impossible to predict in advance because the scope was unknown though the IP has a nominal amount in it for Advance Functionality
The budget for the project was probably invalid at the time of launch at the start because the scope had changed

## Slide 26: Financial Performance & Benefits Review
There was a disconnect between the benefits expected by the business and the project team versus those in the IP (for instance the IP speaks of “a common telephone directory” and yet has no vision of shared services – though it does speak of outsourcing)
The “hidden” outsourcing agenda may have contributed to the lack of business buy in
As previously discussed, the IP was probably out of date at the start and should have been revised

## Slide 27: Training
It is debatable how effective the training was, not through any specific failing on the part of the trainer but probably because:
  The training of customisation was incomplete because the customisation was still in progress at the time of the training
  There were systems failures and other problems
  The training was not contemporaneous with go-live
  There was insufficient emphasis on business process and how they needed to be amended
  There was some push back from the users to the “agreed” processes and work-rounds

## Slide 28: Conclusions & Recommendations
Programme Management: In projects of this scale and risk there should be a Programme Manager with executive authority. It is our belief that this person should be seen to be independent (this does not necessarily, but frequently does, mean external)
Business Strategy: The business strategy must be agreed and clearly communicated to all parties at the start of the project and regularly re-enforced
Project Sponsor/Business Ownership: There must be clear business ownership and an active high profile project sponsor. The sponsor should come from an operating business rather than corporate – it would have been harder for the businesses to disengage
Project Organisation: Clear reporting and accountability is required in project organisation reporting

## Slide 29: Conclusions & Recommendations
Steering Group: Care should be taken when forming Steering Groups that, the members clearly understand their role and are prepared to take tough actions.
  Major projects require Director level SG members but smaller engagements may work more effectively with Senior Managers who are more connected to the day to day business
Project Team: In a multi-business environment business representatives must be of sufficient seniority and representative of all of the known business complexities. Full time secondment must mean just that
Methodology: Projects should have pre-determined methodology sets depending on their complexity and use should be monitored via effective QA reviews or some other means: the role of QA should be as support to the project not policemen

## Slide 30: Conclusions & Recommendations
Long Time-scale Projects: The project should have been formerly re-launched in the summer of 2001
  It would have been better to close or cancel the original project, re-name and re-launch the project
IP Drift: With projects of long duration the IP should be regularly re-evaluated
Project Reporting: Project reporting was copious but did not communicate the essential messages to the key stakeholders
  The format of these reports should be revised and an escalation mechanism devised to ensure that “red flags” are not missed
  When end-users are asked to sign off specifications it is essential that the business process and impact is described adequately such that users know what they are signing up to
  All major decisions must require an affirmative response not an assumption that silence is assent

## Slide 31: Conclusions & Recommendations
Process Review: A comprehensive exercise of mapping current processes at a sufficient level of detail to expose genuine differences should have been undertaken prior to starting development – this would also have forced the debate about harmonising processes and contributed to business buy in
Critical Issues: A method such as “black” or “purple” status should be used to highlight project life threatening issues. When such a “black flag” is raised, the project should be suspended until resolved
Training: Training programmes should be designed from the perspective of the business processes, not the system

## Slide 32: Conclusions & Recommendations
Contract Negotiations:
  The Requirements Document produced by The Supplier was insufficiently detailed and lead to the mixed contracts terms
    All deliverables and customisations known at the time of contract should be scoped sufficiently to lead to a fixed price – had this been done, the complexity in back pay, for example, would have been discovered much earlier
  It would have been better to have one contractual umbrella and a serious of work-packages, rather than many different instruments
  There should be contractual deliverables for all work-packages

## Slide 33: Conclusions & Recommendations
Customisation:
  There should be a documented process to authorise all customisation
  Businesses requesting customisation against the standard process should be required to pay for it and in all but extreme cases be required to wait until “Release 2”
  Legacy support teams (in this case legacy) should be mandatory members of the project team – had this occurred, the surprises that faced the project during testing could have been avoided

## Slide 34: Conclusions & Recommendations
Business Readiness/Deployment: A full time secondment with back fill is required. The manager should have respect of his peer group and sufficient authority to make decisions
The Supplier: Contractual matters are discussed elsewhere. In addition:
  Suppliers should be represented at the Steering Group. Confidential matters can be discussed in separate sessions
  Detailed project financial reporting is needed that can be effectively challenged
  There should be a single supplier of all services – The Supplier should have been made responsible for delivering the reports by sub contracting if necessary, not laying off the risk (which they were contractually entitled to do) to XX Energy